## Sheet1
Sl.No | Date | Time | Activity Title | Activity Description | Error | Error Data | Error Fixed | Status Activity | Deadline
1 | 2020-11-11 | 5:30 | Documentation and repository | Created Repository for the project and Installed eclipse and JDk |  |  |  | Completed
2 | 2020-11-13 | 5:30 | Created the Packages in Eclipse | Created Packages like Config, dao, daoImp, model, View |  |  |  | Completed
3 | 2020-11-16 | 4:30 | Created the class files in Eclipse | Created class files within the model packages. (Except the view package) |  |  |  | completed
4 | 2020-11-17 | 5:30 | Creation of packages | Created Interface files within Dao Package. |  |  |  | Completed
5 | 2020-11-18 | 1:30 | Database Creation | Created Database in MySQL and created 2 tables |  |  |  | Completed
6 | 2020-11-24 | 9:30 | Created UserInterface | Coded for RegistrationFrame and LoginFrame. | Couldn't launch the Application | It shows that there are no recent lauches | yet to fixed | Incomplete
7 | 2020-11-25 | 11:30AM | Database Creation | Created tables for the rest of the database |  |  |  | yet to complete the Employee Id from table 4 and 5
8 | 27/11/2020 - 28/11/2020 | 6:30PM - 11AM | Database Creation | Created all the tables in the Mysql database | Had issues with the foreign key | I had issues with finding out the connctivity between two tables | I found the output now and am good to go | Completed
9 | 2020-11-29 | 1PM - 3PM | Connection of database to the program | Connected the PCSDB with my eclipse, Builded up path for mysql jar file, created the JDBC connection. | Had issues with connecting the database in my mac, but I solved the issue. | connection was not established | I changed my username to root and it worked. | Completed
10 | 2020-11-29 | 4PM-5:30PM | Created class | Built the Employee java class in the model package and completed errors | Had minor issues in creating the program | program can't be executed | Fixed the errors in the program | Completed
11 | 2020-11-30 | 6:30PM - 12PM | Built the class | Built the class for employee dao, employee class, and interface class |  |  |  | completed
12 | 2020-11-02 | 11PM-1AM | Entered the first data into the table | Entered the first Employee detail into the table and connected with SQL workbench |  |  |  | Completed
13 | 2020-11-03 | 6:30PM - 11AM