## Sheet1
Sl.No | Date | Time | Activity Title | Activity Description | Error | Error Data | Error Fixed | Status Activity | Deadline
1 | 2020-11-11 | 5:30 | Documentation and repository | Created Repository for the project and Installed eclipse and JDk |  |  |  | Completed
2 | 2020-11-13 | 5:30 | Created the Packages in Eclipse | Created Packages like Config, dao, daoImp, model, View |  |  |  | Completed
3 | 2020-11-16 | 4:30 | Created the class files in Eclipse | Created class files within the model packages. (Except the view package) |  |  |  | completed
4 | 2020-11-17 | 5:30 | Creation of packages | Created Interface files within Dao Package. |  |  |  | Completed
5 | 2020-11-18 | 1:30 | Database Creation | Created Database in MySQL and created 2 tables |  |  |  | Completed
6 | 2020-11-24 | 9:30 | Created UserInterface | Coded for RegistrationFrame and LoginFrame. | Couldn't launch the Application | It shows that there are no recent lauches | yet to fixed | Incomplete
7 | 2020-11-25 | 11:30Am | Database Creation | Created tables for the rest of the database |  |  |  | yet to complete the Employee Id from table 4 and 5